## Overall Budget
Project Lab 1 - ECE 3331-302 | Managed Total |  |  | Total Estimate |  |  | Start Date | 2023-08-29
Direct Labor: | [6 empty] | Today | 2023-09-26
Category: | Rate/Hr | Hrs |  | Rate/Hr | Hrs
Christian Maldonado | 15 | 52 | 780 | 15 | 48 | 720 | End Date | 2023-09-26
Jeffrey Saied | 15 | 53 | 795 | 15 | 48 | 720
Robert Sherrick | 15 | 52 | 780 | 15 | 48 | 720
DL Subtotal (DL) |  | Subtotal: | 2355 |  | Subtotal: | 2160
Labor Overhead | rate: | 100% | 2355 | rate: | 100% | 2160
Total Direct Labor (TDL) |  |  | 4710 |  |  | 4320
Contact Labor:
Lab Assistant | 40 | 3 | 120 | 40 | 20 | 800
Landon (Student) | 15 | 1 | 15 | 15 | 1 | 15
Silas (Student) | 15 | 5 | 75 | 15 | 5 | 75
Total Contract Labor (TCL) |  |  | 210 |  |  | 890
Direct Material Costs: |  |  | 343.73 |  |  | 350
(from Material Cost worksheet)
Total Direct Material Cost: (TDM) |  |  | 343.73 |  |  | 350
Equipment Rental Cost: | Value | Rental Rate |  | Value | Rental Rate |  | Date begin | Date end/today | Total rental days
Tektronix TDS Oscillioscope | 520 | 0.2% | 15.6 | 520 | 0.2% | 15.6 | 2023-09-11 | 2023-09-25 | 15
Mastech Power Supply (HY3005D) | 220 | 0.2% | 6.6 | 220 | 0.2% | 6.6 | 2023-09-11 | 2023-09-25 | 15
BK Precision Function Generator | 490 | 0.2% | 14.7 | 490 | 0.2% | 14.7 | 2023-09-11 | 2023-09-25 | 15
Tenima Digital Soldering Station | 80 | 0.2% | 4.48 | 80 | 0.2% | 4.48 | 2023-08-29 | 2023-09-25 | 28
Total Rental Costs: (TRM) |  |  | 41.38 |  |  | 41.38
Total TDL+TCL+TDM+TRM |  |  | 5305.11 |  |  | 5601.38
Business overhead |  | 55% | 2917.81 |  | 55% | 3080.76
Total Cost: |  | Current | 8222.92 |  | Estimate | 8682.14
SUMMARY:
Labor + OH | 4710
Contract Labor | 210
Materials & Equip Rental | 385.11
Overhead | 2917.81
TOTAL | 8222.92

## Labor Hours
DATE | Christian M | Jeffrey S | Robert S | Lab Asst. | Silas (Stud.) | Landon (Stud.) | Total Hours
2023-08-29 | 1 | 2 | 0 |  |  |  | Christian | 52
2023-08-30 | 2 | 1 | 3 |  |  |  | Jeffrey | 53
2023-08-31 | 0 | 0 | 2 |  |  |  | Robert | 52
2023-09-01 | 0 | 3 | 0 |  |  |  | Lab Asst. | 3
2023-09-02 | 3 | 0 | 0 |  |  |  | Silas | 5
2023-09-03 | 2 | 2 | 2 |  |  |  | Landon | 1
2023-09-04 | 3 | 3 | 3
2023-09-05 | 0 | 4 | 4
2023-09-06 | 1 | 2 | 2 | 1
2023-09-07 | 2 | 2 | 0
2023-09-08 | 1 | 0 | 2
2023-09-09 | 0 | 0 | 0
2023-09-10 | 3 | 5 | 5
2023-09-11 | 4 | 2 | 0
2023-09-12 | 4 | 4 | 4
2023-09-13 | 1 | 2 | 0 |  |  | 1
2023-09-14 | 5 | 3 | 9 |  | 5
2023-09-15 | 2 | 2 | 0
2023-09-16 | 3 | 0 | 0
2023-09-17 | 0 | 2 | 4
2023-09-18 | 3 | 2 | 2
2023-09-19 | 0 | 0 | 0
2023-09-20 | 0 | 0 | 0
2023-09-21 | 1 | 2 | 2
2023-09-22 | 1 | 1 | 1
2023-09-23 | 1 | 0 | 2
2023-09-24 | 4 | 4 | 0 | 2
2023-09-25 | 5 | 5 | 5
2023-09-26 | 0 | 0 | 0

## Material Costs
Name | Cost | quantity | notes/websites | purchase date | total | TOTAL
H-Bridge (Total Components) | 40.81 | 36 | mouser.com | 2023-08-29 | 343.73 | 343.73
H-Bridge Greenboard + Shipping | 7.41 | 1 | aliexpress.com | 2023-08-29
Basys 3 Board | 170 | 1 | digilent.com | 2023-09-01
Rover Chassis | 75 | 1 | amazon.com | 2023-09-01
Plusivo Digital Multimeter | 12.74 | 1 | amazon.com | 2023-09-11
Elego (HB-V2) Power Supply | 9.55 | 1 | amazon.com | 2023-09-14
10k Resistor (CMF6510k) | 1.26 | 1 | mouser.com | 2023-09-14
2.2k Resistor (CFR250) | 0.21 | 1 | mouser.com | 2023-09-14
1.1k Resistor (CMF501k) | 1.24 | 2 | mouser.com | 2023-09-14
LM339N Comparator Component | 0.3 | 1 | mouser.com | 2023-09-14
GNA Fuse Kit | 7.56 | 1 | amazon.com | 2023-09-17
Wire Kit | 5.3 | 1 | amazon.com | 2023-09-17
Energizer 9V2 Duo Battery Pack | 7.35 | 1 | amazon.com | 2023-09-17
3D Printer Model's | 5 | 2 | Noah Bazar | 2023-09-23