## Overall Budget
Project Lab B - ECE 3332-301 | Managed Total |  |  | Total Estimate |  |  | Start Date | 2024-05-30
Direct Labor: | [6 empty] | Today | 2024-07-25
Category: | Rate/Hr | Hrs |  | Rate/Hr | Hrs
Tarek Darwiche | 15 | 95 | 1425 | 15 | 96 | 1440 | End Date | 2024-07-25
Dylan Pitcher | 15 | 95 | 1425 | 15 | 96 | 1440
Christian Maldonado | 15 | 95 | 1425 | 15 | 96 | 1440
Jeffrey Saied | 15 | 96 | 1440 | 15 | 96 | 1440
DL Subtotal (DL) |  | Subtotal: |  |  | Subtotal:
Labor Overhead | rate: | 100% | 5715 | rate: | 100% | 5760
Total Direct Labor (TDL) |  |  | 11430 |  |  | 11520
Contact Labor:
Student(s) | 15 | 0 | 0 | 15 | 16 | 240
Total Contract Labor (TCL) |  |  | 0 |  |  | 240
Direct Material Costs: |  |  | 194.53 |  |  | 100
(from Material Cost worksheet)
Total Direct Material Cost: (TDM) |  |  | 194.53 |  |  | 100
Equipment Rental Cost: | Value | Rental Rate |  | Value | Rental Rate |  | Date begin | Date end/today | Total rental days
Raspberry Pi 4 Model B | 45 | 0.2% | 4.68 | 45 | 0.2% | 4.68 | 2024-06-03 | 2024-07-25 | 52
Waveform Generator | 1112 | 0.2% | 115.65 | 1112 | 0.2% | 115.65 | 2024-06-03 | 2024-07-25 | 52
Digital Storage Oscilloscope | 999 | 0.2% | 103.9 | 999 | 0.2% | 103.9 | 2024-06-03 | 2024-07-25 | 52
Multimeter | 844 | 0.2% | 87.78 | 844 | 0.2% | 87.78 | 2024-06-03 | 2024-07-25 | 52
SIM7600A-H 4G HAT | 53.99 | 0.2% | 4.65 | 53.99 | 0.2% | 4.65 | 2024-06-12 | 2024-07-25 | 43
iBKS 105 BT Beacons | 179.7 | 0.2% | 17.26 | 179.7 | 0.2% | 17.26 | 2024-06-07 | 2024-07-25 | 48
HDMI + USB Touch Display | 35.99 | 0.2% | 2.52 | 35.99 | 0.2% | 2.52 | 2024-06-20 | 2024-07-25 | 35
Total Rental Costs: (TRM) |  |  | 336.44 |  |  | 336.44
Total TDL+TCL+TDM+TRM |  |  | 11960.97 |  |  | 12196.44
Business overhead |  | 55% | 6578.54 |  | 55% | 6708.04
Total Cost: |  | Current | 18539.51 |  | Estimate | 18904.48
SUMMARY:
Labor + OH | 11430
Contract Labor | 0
Materials & Equip Rental | 530.97
Overhead | 6578.54
TOTAL | 18539.51

## Labor Hours
WEEK | Tarek D | Dylan P | Christian M | Jeffrey S | Total Hours
5/30/2024 - 6/6/2024 | 13 | 14 | 14 | 12 | Tarek | 95
6/7/2024 - 6/13/2024 | 15 | 13 | 15 | 16 | Dylan | 95
6/14/2024 - 6/20/2024 | 14 | 14 | 13 | 13 | Christian | 95
6/21/2024 - 6/27/2024 | 16 | 15 | 17 | 16 | Jeffrey | 96
6/28/2024 - 7/4/2024 | 5 | 5 | 4 | 4 | Total Hrs | 381
7/5/2024 - 7/11/2024 | 4 | 5 | 4 | 7
7/12/2024 - 7/18/2024 | 12 | 14 | 13 | 15
7/19/2024 - 7/25/2024 | 16 | 15 | 15 | 13

## Material Costs
Name | Cost | quantity | notes/websites | purchase date | total | TOTAL
32GB Micro SD Card | 8.98 | 1 | Walmart | 2024-06-03 | 194.53 | 194.53
Micro HDMI to HDMI Adapter | 9.88 | 1 | Walmart | 2024-06-03
NEO-6M GPS Module | 8.99 | 1 | Amazon | 2024-06-03
USB PD Trigger Board | 6.66 | 5 | AliExpress | 2024-06-12
AWM DSI Ribbon Cable | 6.46 | 1 | Amazon | 2024-06-16
12V 5.2A Rechargable Battery | 32.99 | 1 | Amazon | 2024-06-19
5V 3A Step Down Power Module | 8.99 | 5 | Amazon | 2024-06-22
USB to USB-C Cable | 2.99 | 1 | Walmart | 2024-06-25
CR2477 3V Li-Ion Battery | 6.15 | 8 | Amazon | 2024-07-09
SIM Card (Preordered 4G Network) | 65 | 1 | T-Mobile | 2024-07-09
Top & Bottom 3D Casing | 37.44 | 2 | TTU Library | 2024-07-21

## Bill of Materials
Name | Amount
Raspberry Pi 4 Model B (4GB) | 1
32GB MicroSD Card (Preinstalled RPi OS) | 1
HDMI + USB Touch Display (Bookworked OSK) | 1
NanoHDMI to HDMI Adapter | 1
HDMI Cable | 1
USB to USB-C Cable | 1
MicroUSB to USB Cable | 1
SIM7600A-H 4G HAT Module (Total Components) | 1
SIM Card (Preordered 4G Network) | 1
LTC4056 Step Down Power Module (Total Components) | 1
12V 5.2A Rechargable Battery + Cable I/O Connector | 1
iBKS 105 Bluetooth Beacon | 8
CR2477 3V Li-Ion Battery | 8
3D Printed Top Model Casing | 1
3D Printed Bottom Model Casing | 1