## Overall Budget
ECE 3334-301 | Managed Total |  |  | Total Estimate |  |  | Start Date | 2024-09-03
Direct Labor: | [6 empty] | Today | 2024-12-03
Category: | Rate/Hr | Hrs |  | Rate/Hr | Hrs
Christian Maldonado | 25 | 112 | 2800 | 25 | 165 | 4125 | End Date | 2024-12-03
Jack Sims | 25 | 121 | 3025 | 25 | 165 | 4125
Dylan McKeon | 25 | 111 | 2775 | 25 | 165 | 4125
Robert Sherrick | 25 | 131 | 3275 | 25 | 165 | 4125
DL Subtotal (DL) |  | Subtotal: | 11875 |  | Subtotal: | 16500
Labor Overhead | rate: | 100% | 11875 | rate: | 100% | 16500
Total Direct Labor (TDL) |  |  | 23750 |  |  | 33000
Contact Labor:
Faculty | 200 | 0 | 0 | 200 | 2 | 400
Lab Assistant(s) | 40 | 0 | 0 | 40 | 5 | 200
Students (Lab I) | 15 | 0 | 0 | 15 | 3 | 45
Student(s) (Lab II) | 20 | 0 | 0 | 20 | 3 | 60
Student(s) (Lab III) | 25 | 0 | 0 | 25 | 5 | 125
Student(s) (Lab IV) | 30 | 0 | 0 | 30 | 8 | 240
Total Contract Labor (TCL) |  |  | 0 |  |  | 1070
Direct Material Costs: |  |  | 179.45 |  |  | 500
(from Material Cost worksheet)
Total Direct Material Cost: (TDM) |  |  | 179.45 |  |  | 500
Equipment Rental Cost: | Value | Rental Rate |  | Value | Rental Rate |  | Date begin | Date end/today | Total rental days
Tektronix TDS Oscillioscope | 520 | 1% | 67.6 | 520 | 1% | 67.6 | 2024-09-03 | 2024-11-12 | 91
Mastech Power Supply (HY3005D) | 220 | 1% | 28.6 | 220 | 1% | 28.6 | 2024-09-03 | 2024-11-12 | 91
BK Precision Function Generator | 490 | 1% | 63.7 | 490 | 1% | 63.7 | 2024-09-03 | 2024-11-12 | 91
Tenima Digital Soldering Station | 80 | 1% | 10.4 | 80 | 1% | 10.4 | 2024-09-03 | 2024-11-12 | 91
Total Rental Costs: (TRM) |  |  | 170.3 |  |  | 170.3
Total TDL+TCL+TDM+TRM |  |  | 24099.75 |  |  | 34740.3
Business overhead |  | 55% | 13254.87 |  | 55% | 19107.17
Total Cost: |  | Current | 37354.62 |  | Estimate | 53847.47
SUMMARY:
Labor + OH | 23750
Contract Labor | 0
Materials & Equip Rental | 349.75
Overhead | 13254.87
TOTAL | 37354.62

## Labor Hours
DATE | Christian M | Jack S | Robert S | Dylan M | Total Hours
9/3/2024 - 9/10/2024 | 6 | 8 | 7 | 6 | Christian | 112
9/11/2024 - 9/17/2024 | 9 | 9 | 8 | 6 | Jack | 121
9/18/2024 - 9/24/2024 | 6 | 7 | 12 | 5 | Robert | 131
9/25/2024 - 10/1/2024 | 4 | 10 | 10 | 9 | Dylan | 111
10/2/2024 - 10/8/2024 | 11 | 13 | 10 | 10 | Total | 475
10/9/2024 - 10/15/2024 | 7 | 7 | 7 | 7
10/16/2024 - 10/22/2024 | 8 | 8 | 8 | 8
10/23/2024 - 10/29/2024 | 9 | 10 | 12 | 9
10/30/2024 - 11/5/2024 | 5 | 8 | 14 | 9
11/6/2024 - 11/12/2024 | 11 | 7 | 8 | 9
11/13/2024 - 11/19/2024 | 23 | 20 | 25 | 20
11/20/2024 - 11/26/2024 | 7 | 8 | 6 | 7
11/27/2024 - 12/3/2024 | 6 | 6 | 6 | 6

## Material Costs
Name | Cost | quantity | notes/websites | purchase date | total | TOTAL
deAO Train Set | 16.23 | 2 | amazon | 2024-09-09 | 32.46 | 179.45
HiLetgo | 10.27 | 4 | amazon | 2024-09-12 | 10.27
USB Rechargeable 9V Li-ion Battery | 20.67 | 4 | amazon | 2024-09-11 | 20.67
Raspberry Pi 4 Model B | 40 | 1 | amazon | 2024-09-16 | 40
Raspberry Pi Pico W | 18.65 | 2 | amazon | 2024-09-11 | 37.3
Rotary Encoder | 2.12 | 2 | mouser | 2024-09-27 | 4.24
Adafruit H-Bridge | 1.5 | 2 | mouser | 2024-10-01 | 3
LM311P Comparator | 0.58 | 2 | mouser | 2024-10-08 | 1.16
HiLetgo Card Sensor Module 3-Pack | 9.99 | 2 | amazon | 2024-11-10 | 21.56
HiLetgo 10pcs IP Infrared | 8.79 | 1 | amazon | 2024-11-10 | 8.79

## Bill of Materials
Name | quantity
deAO Train Set | 2
HiLetgo MFRC522 RFID Reader | 1
HiLetgo HW-201 IR Sensor | 1
USB Rechargeable 9V Li-ion Battery | 1
Raspberry Pi 4 Model B | 1
Raspberry Pi Pico W | 2
Rotary Encoder | 2
L9110H H-Bridge | 2
MG995 Servo Motor | 1
3D-Printed Track Sections | 2